## Sheet1
Gantt Chart for Project Management
|  |  | ESTIMATED |  | ACTUAL |  |  | TIME (Hours)
# | ACTIVITIES | RESOURCES | START | DUR | START | DUR | % | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | COMMENTS
1 | Activity 1 | George, VizWik | 1 | 2 | 1 | 3 | 100% | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Took longer, due to software glitch
2 | Activity 2 | Alice, Inkscape | 2 | 4 | 2 | 3 | 100% | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | Completed faster, expert artist
3 | Activity 3 | Frank, Inkscape | 2 | 3 | 1 | 2 | 100% | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Completed earlier, available early
4 | Activity 4 | Betty, MS Word | 2 | 5 |  |  | 50% | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | Not yet completed, behind schedule
5 | Activity 5 | Betty, VizWik | 3 | 6 |  |  | 0% | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | Not yet started
6 | Activity 6 | Alice, MS Word | 3 | 4 |  |  | 35% | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Underway and on time
7 | Activity 7 | Frank, MS Word | 3 | 5 |  |  | 75% | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | Underway and ahead of schedule
8 | Activity 8 | George, Inkscape | 4 | 7 |  |  | 0% | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | Not yet started
9 | Activity 9 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Activity 10 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Activity 11 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Activity 12 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Activity 13 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Activity 14 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Activity 15 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Activity 16 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Activity 17 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Activity 18 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Activity 19 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Activity 20 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0